## Sheet1
C2 Regression
Tool & Content Areas | Task ID | Assignment | Testing Status | Defects Logged | Further Review?
Site Manager
View Website | 14244 | Kate | Open
Community & Support Link | 14244 | Kate | Open
Feedback | 14244 | Kate | Open
Signout | 14244 | Kate | Open
Navigation menu | 14244 | Kate | Open
Footer Links | 14244 | Kate | Open
How Do I Tab.. |  |  | Done
Users & Groups
Users
Users | 14135 | Bibo | Done
Passports | 14135 | Bibo | Done
Import Users | 14135 | Bibo | Done
Update Users | 14135 | Bibo | Done
Import Family Relationships | 14135 | Bibo | In Progress
Recycle Bin | 14135 | Bibo | Done
Groups
Groups | 14136 | Kate | Done
Categories | 14136 | Kate | Done
Import Groups | 14136 | Kate | In progress
Mass Assign Users | 14136 | Kate | In progress
Settings
User Settings | 14137 | Kate | Done
LDAP Settings | 14137 | Kate | Done
Configure |  |  | done
Sites |  |  | Done
Sites | 13950 | Bibo | Done
Channel Library |  | Bibo | Done
Channel Library | 13950 | Bibo | Done
Section Assets |  |  | Done
Page Types | 13950 | Bibo | Done
Editor Layouts | 13950 | Bibo | Done
Section Configurations | 13950 | Bibo | Done
Calendar Assets |  |  | Done
Event Categories | 13950 | Bibo | Done
Collections | 13950 | Bibo | Done
Templates
Template Library | 14237 | Bibo | Open
Custom Templates | 14238 | Bibo | Open
Apps |  |  | Done
System Apps | 13950 | Bibo | Done
Custom Apps | 13950 | Bibo | Done
PassKeys |  |  | Done
PassKeys | 13950 | Bibo | Done
Suggestions | 13950 | Bibo | Done
Blocked | 13950 | Bibo | Done
MyView |  |  | Done
Configurations | 13950 | Bibo | Done
Viewers | 13950 | Bibo | Done
Universal Connector |  | Bibo | Done
Connectors | 13950 | Bibo | Done
Smartphone App |  | Bibo | Done
Actions | 13950 | Bibo | Done
Mobile Notification, Mobile on/off, Mobile Banner | 13950 | Bibo | Done
System Settings |  | Bibo | Done
Settings | 13950 | Bibo | Done
Content Moderation
Approval Queue | 13961 | Bibo | Done
Moderated Groups | 13961 | Bibo | Done
Site & Channels
Home Tab (any workspace)
Home Tab | 13962 | Kate | Done
Site Workspace
Header
Header Content & Site Settings | 13962 | Kate | Done
Summary Tab
Homepage | 13962 | Kate | Done
Calendar | 13945 | Allen | Open
Common Tools | 13962 | Kate | Done
Pending Comments | 13962 | Kate | Done
Total Visits | 13962 | Kate | Done
SW Ads area | 13962 | Kate | Done
Mobile Tab
Actions | 13962 | Kate | Done
Mobile notification, Status | 13962 | Kate | Done
Tools Tab
Files & Folders | 13962 | Kate | Done
Broadcast E-Alerts | 13962 | Kate | Done
Section Robot | 14248 |  | Open
Approve Community Editing | 13962 | Kate | Done
Reports | 14239 |  | Open
Minibase | 13962 | Kate | Done
Friendly Web Address Mappings | 13962 | Kate | Done
Forms & Surveys |  | New Story
Approve Visitor Comments | 13962 | Kate | Done
App Manager | 13962 | Kate | Done
Photo Gallery | 13962 | Kate | Done
Directors & Viewers Tab
Site Directors, Homepage Editors & Viewers | 13962 | Kate | Done
Channels Tab
Assigned Channels | 13962 | Kate | Done
Statistics Tab
Site Statistics | 13962 | Kate | Done
Channel Workspace
Summary Tab
Homepage | 13962 | Kate | Done
Calendar | 13945 | Allen | Open
Sections | 13962 | Kate | Done
Pending Comments | 13962 | Kate | Done
Total Visits | 13962 | Kate | Done
Tools Tab
Files & Folders | 14251 |  | Open
Approve Visitor Comments | 13962 | Kate | Done
App Manager | 13962 | Kate | Done
Photo Gallery | 13962 | Kate | Done
Forms & Surveys |  | New Story
Approve Community Editing | 13962 | Kate | Done
Reports | 14239 |  | Open
Minibase | 13962 | Kate | Done
Directors & Viewers
Channel Directors & Viewers | 13962 | Kate | Done
Statistics
Channel Statistics | 13962 | Kate | Done
Section Workspace
Summary Tab
Current Pages | 14257 | Kate | Open
Common Tools | 14257 | Kate | Open
Pending Comments | 14257 | Kate | Open
Total visists | 14257 | Kate | Open
Tools Tab
Files & Folders | 14251 | Kate | Open
Approve Visitor Comments | 13962 | Kate | Done
App Manager | 13962 | Kate | Done
Photo Gallery | 13962 | Kate | Done
Forms & Surveys |  | New Story
Approve Community Editing | 13962 | Kate | Done
Reports | 14239 |  | open
Minibase | 13962 | Kate | Done
Editors & Viewers
Section Editors | 14258 | Kate | open
Viewers | 14258 | Kate | open
Membership Tab
Section Members | 14259 | Kate | open
Section Image | 14259 | Kate | open
Common Tools | 14259 | Kate | open
Statistics Tab
Section Statistics | 14247 | Kate | open
Apps - SM View
About Teacher | 12260 | Bibo | open
Alumni Directory | 13962 | Kate | Done
Announcements | 13962 | Kate | Done
Article Library | 13962 | Kate | Done
Assignment | 13962 | Kate | Done
Blog | 13962 | Kate | Done
Book List | 13962 | Kate | Done
Calendar | 13945 | Allen | Open
Discussion | 13962 | Kate | Done
Document Viewer | 12260 | Bibo | open
Embed Code | 12260 | Bibo | open
Facebook-like | 12260 | Bibo | open
File Library | 13962 | Kate | Done
Flex Editor | 14253 |  | Open
Furtal | In House |  | open
Headlines & Features | 13962 | Kate | Done
Link Library | 13962 | Kate | Done
Lunch Menu | 13962 | Kate | Done
Maps and Directions | 13962 | Kate | Done
Minibase | 14255 |  | Open
Photo Gallery | 14254 |  | Open
Podcast | 13962 | Kate | Done
Q&A | 13962 | Kate | Done
School Directory | 14260 | Bibo | Open
Site Shortcuts | 14261 |  | Open
Staff Directory | 14260 | Bibo | Open
Twitter Share | 14260 | Bibo | Open
Upcoming Events | 13962 | Kate | Done
Wiki | 13962 | Kate | Done
End User
MyStart Bar
District Home button | 14262 |  | Open
Select a School drop down menu | 14262 |  | Open
Register | 14262 |  | Open
Search Site | 14262 |  | Open
Sign In | 14262 |  | Open
Site Manager | 14262 |  | Open
My PassKeys | 14262 |  | Open
My Account
Information | 14264 |  | Open
E-Alert Settings | 14264 |  | Open
Subscriptions | 14264 |  | Open
PassKey Accounts | 14264 |  | Open
School Associations | 14264 |  | Open
Connected Services | 14264 |  | Open
Change Password | 14264 |  | Open
Delete Account | 14264 |  | Open
Sign Out | 14264 |  | Open
Navigation
Channel Bar & Dropdown menus | 14265 |  | Open
Directory page | 14265 |  | Open
Section Pages, Heirachy & Imagery | 14265 |  | Open
Classic Heirarchy | 14265 |  | Open
Breadcrumbs | 14265 |  | Open
Site Map | 14265 |  | Open
Footer Links | 14265 |  | Open
Pages
Breadcrumbs | 14266 |  | Open
Layouts | 14266 |  | Open
Footer Links | 14266 |  | Open
Left Nav | 14266 |  | Open
Sub Page / Subpage no nav | 14266 |  | Open
Misc
Active Blocks - Template | 14268
Flex Editor Active Blocks | 14267 |  | Open
Flex Editor Simple Embed | 14267 |  | Open
Flex Editor Complex Embed | 14267 |  | Open
Check for other embed, etc in Flex editor | 14267 |  | Open
Apps (list & detail view; social components)
About Teacher | 14273 |  | open
Alumni Directory | 14273 |  | open
Announcements | 14273 |  | open
Article Library | 14273 |  | open
Assignment | 14273 |  | open
Blog | 14274 |  | open
Book List | 14274 |  | open
Calendar |  |  | open
Discussion | 14274 |  | open
Document Viewer | 14274 |  | open
Embed Code | 14274 |  | open
Facebook-like | 14274 |  | open
File Library | 14274 |  | open
Flex Editor | 14267 |  | Open
Inline editor (flex editor) | 14267 |  | Open
Furtal | In house |  | Open
Headlines & Features | 14277 |  | Open
Link Library | 14277 |  | Open
Lunch Menu | 14277 |  | Open
Maps and Directions | 14277 |  | Open
Minibase | 14276 |  | Open
Photo Gallery | 14275 |  | Open
Podcast | 14277 |  | Open
Q&A | 14277 |  | Open
School Directory | 14278 |  | Open
Site Shortcuts | 14279 |  | Open
Staff Directory | 14278 |  | Open
Twitter Share | 14278 |  | Open
Upcoming Events | 14279 |  | Open
Wiki | 14278 |  | Open
Social Components
Community Editing | 14269 |  | open
Commenting | 14269 |  | open
Rating | 14269 |  | open
RSS Feeds | 14269 |  | open
Sidebar
Display Date Grouping | 14270 |  | open
Display Tag List | 14270 |  | open
MyView Workspace
Dashboard
Follow button | 14271 |  | Open
My Gadgets | 14271 |  | Open
New Tab | 14271 |  | Open
Footer Links | 14271 |  | Open
Planner
My Planner | 14272 |  | Open
Child Planners | 14272 |  | Open
Gadgets
Announcements | 14280 |  | Open
Global Shortcuts | 14280 |  | Open
Lunch Menu | 14280 |  | Open
Minibase Search | 14280 |  | Open
Nimbus Activity | 14281 |  | Open
Nimbus Groups | 14281 |  | Open
Nimbus Recent Messages | 14281 |  | Open
PassKeys | 14282 |  | Open
Personal Shortcuts | 14282 |  | Open
Planner Events (my events, my children) | 14282 |  | Open
RSS Reader | 14282 |  | Open
Section Membership | 14282 |  | Open
Synergy Comments | 14283 |  | Open
Synergy Favorites | 14283 |  | Open
Synergy File Uploader | 14283 |  | Open